## All partners together
All partners together |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 483.5 | 2369.5 | 307.5 | 3160.5 | 465.7333 | 14.74% | 36 | 48 | 80 | 123 | 155 | 124 | 131 | 103 | 97 | 35 | 55 | 94 | 68 | 75 | 100 | 128 | 144 | 127 | 97 | 80 | 81 | 45 | 66 | 96 | 49 | 54 | 67 | 87 | 127 | 156 | 179 | 194 | 86 | 63 | 121 | 122 | 1081 | 1107 | 1305
WP1 | Preparation |  | 82 | 474 | 32.5 | 588.5 | 57.0667 | 9.697% | 2 | 8 | 38 | 44 | 44 | 0 | 0 | 5 | 9 | 0 | 22 | 31 | 4 | 7 | 11 | 7 | 4 | 2 | 4 | 14 | 22 | 5 | 23 | 26 | 8 | 10 | 14 | 8 | 10 | 1 | 8 | 6 | 17 | 2 | 6 | 6 | 203 | 129 | 96
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 18.62% | 12.25% |  |  |  | 2 | 2 | 2 | [5 empty] | 2 | 1 | 1 | 1 | [11 empty] | 2 | 3 | 3 | [8 empty] | 9 | 2 | 8
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [7 empty] | 2 | 2 | 2 | 2 | [5 empty] | 2 | 2 | [13 empty] | 2 | 3 | 3 | [8 empty] | 12 | 0 | 8
A | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [7 empty] | 2 |  |  | 2 | [5 empty] | 2 | 2 |  |  | 2 |  | 2 |  | 2 |  | 2 |  |  | 2 | 2 | 2 | [6 empty] | 2 |  | 2 | 2 | 8 | 10 | 10
L | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [7 empty] | 2 | 2 | 2 | 2 | [5 empty] | 2 | 2 |  | 2 | [8 empty] | 2 | 2 | [12 empty] | 12 | 6 | 0
L | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [8 empty] | 5 | 5 | [6 empty] | 2 | 2 | [7 empty] | 2 | 4 | [10 empty] | 2 | 2 |  |  |  | 14 | 6 | 4
| WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [6 empty] | 2 | 2 | [10 empty] | 1 | 2 | 1 |  | 1 |  | 1 |  | 1 |  |  | 1 | 1 | 1 | [10 empty] | 4 | 8 | 2
T | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [9 empty] | 5 | 6 | [5 empty] | 1 | 2 |  |  | 7 | 7 | [10 empty] | 2 |  | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 14 | 14 | 14
O | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [8 empty] | 6 | 6 | 6 | [7 empty] | 2 | 2 | [22 empty] | 18 | 4 | 0
G | WP1.3/T1.3.1 (Kaye) | Training units for teachers | [8 empty] | 5 | 5 | 5 | [5 empty] | 5 | 5 | [7 empty] | 4 | 4 |  | 5 | 5 |  |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 25 | 18 | 8
E | WP1.3/T1.3.2 (Kaye) | Training units for mentors | [8 empty] | 5 | 5 | 5 |  |  | 5 | 5 |  | 5 | 5 | [7 empty] | 4 | 4 |  | 5 | 5 |  |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 35 | 18 | 8
T | WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [8 empty] | 2 | 3 | 3 | [5 empty] | 1 | 2 | [7 empty] | 4 | 4 |  | 5 | 5 | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 11 | 18 | 10
H | WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [33 empty] | 2 | 2 |  |  | 2 | 3 |  |  |  | 0 | 0 | 9
E | WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [8 empty] | 7 | 7 | 7 | [6 empty] | 8 | [9 empty] | 4 | 5 | 5 | 1 | 1 |  |  |  | 1 | [6 empty] | 29 | 14 | 3
R | WP1.3/T1.3.6 (Kaye) | Policy makers | [10 empty] | 2 |  |  |  | 2 | [5 empty] | 1 |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 2 | 2 | [8 empty] | 2 | 2 | 4 | 7 | 8
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [8 empty] | 2 | 2 | 2 |  |  |  | 2 | [8 empty] | 2 |  |  | 2 | [10 empty] | 2 | 2 |  |  |  | 8 | 4 | 4
WP2 | Development |  | 143.5 | 1261 | 45.5 | 1450 | 179.0667 | 12.35% | 4 | 10 | 10 | 35 | 66 | 73 | 87 | 48 | 37 | 4 | 4 | 28 | 26 | 26 | 36 | 51 | 66 | 56 | 31 | 26 | 19 | 2 | 9 | 26 | 2 | 1 | 7 | 21 | 62 | 101 | 122 | 131 | 12 | 0 | 52 | 52 | 406 | 374 | 563
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 45.88% | 38.45% | [5 empty] | 8 | 8 | 8 | 10 | 10 |  |  | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | 5 |  |  |  |  | 10 | 20 | 30 | 40 | 1 |  | 5 | 5 | 52 | 50 | 111
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [10 empty] | 5 | 5 | 4 | 5 | 5 |  |  | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 |  | 1 |  | 1 |  | 1 |  | 1 | 1 |  | 5 | 5 | 28 | 20 | 15
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [10 empty] | 8 | 8 | 6 | 8 | 8 |  |  | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 |  |  |  |  | 10 | 20 | 30 | 40 | 1 |  | 10 | 10 | 44 | 40 | 121
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [6 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | [10 empty] | 5 | 5 | 40 | 30 | 10
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [7 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [12 empty] | 62 | 24 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [9 empty] | 5 | 10 | 12 | 19 | [7 empty] | 10 | 20 | 30 | 20 | [9 empty] | 10 | 20 | 30 | 20 |  | 1 |  | 10 | 5 | 46 | 80 | 96
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [9 empty] | 5 | 10 | 12 | 19 | [5 empty] | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 |  |  | 4 |  |  |  |  | 10 | 20 | 30 | 40 |  |  | 5 | 8 | 46 | 35 | 113
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [9 empty] | 5 | 5 | 5 | 5 | [5 empty] | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 |  |  | 3 | 2 | [8 empty] | 1 |  | 5 | 7 | 20 | 25 | 13
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [9 empty] | 5 | 5 | 5 | 5 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 |  |  | 5 | 10 | 10 | 5 |  |  |  |  | 5 | 5 | 20 | 20 | 40
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [9 empty] | 5 | 5 | 5 | 5 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | 2 | 20 | 20 | 14
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [11 empty] | 3 | 6 | 15 | 4 | [6 empty] | 5 | 10 | 10 | 5 | [10 empty] | 5 | 10 | 10 | 5 |  |  |  | 28 | 30 | 30
WP3 | Quality Plan |  | 43 | 219.5 | 3 | 265.5 | 27.0667 | 10.19% | 0 | 0 | 0 | 8 | 9 | 12 | 7 | 12 | 16 | 2 | 0 | 2 | 2 | 2 | 12 | 15 | 15 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 11 | 11 | 11 | 5 | 6 | 6 | 3 | 3 | 4 | 0 | 68 | 67 | 68
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 8.401% | 5.812% |  |  |  |  | 2 | 3 | 5 |  | 2 | 2 | [5 empty] | 3 | 4 | 4 | [9 empty] | 2 | 2 | 2 | [7 empty] | 14 | 11 | 6
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [9 empty] | 2 | 2 | 2 | 2 | 2 | 3 | [5 empty] | 3 | 4 | 4 | [9 empty] | 3 | 3 | 3 | [7 empty] | 13 | 11 | 9
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [9 empty] | 4 | 4 | 5 | 5 | 6 | 7 | [5 empty] | 3 | 4 | 4 | [9 empty] | 2 | 2 | 2 | [7 empty] | 31 | 11 | 6
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [13 empty] | 2 | 4 | 2 |  | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 6 | 6 | 3 | 3 | 4 |  | 10 | 34 | 47
WP4 | Dissemination & Exploitation |  | 62 | 342 | 2.5 | 406.5 | 38.5333 | 9.479% | 0 | 0 | 2 | 4 | 6 | 8 | 7 | 7 | 5 | 1 | 0 | 3 | 6 | 10 | 11 | 12 | 13 | 16 | 4 | 5 | 7 | 6 | 2 | 10 | 5 | 9 | 5 | 15 | 13 | 18 | 13 | 20 | 14 | 14 | 9 | 9 | 43 | 102 | 144
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 12.86% | 8.274% |  |  |  |  | 2 | 3 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 | 15 | 12 | 18
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [8 empty] | 2 | 2 | 1 | 1 | 1 | 1 | 1 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 3 | 4 | 5 | 5 |  | 11 | 8 | 23
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [10 empty] | 2 | 3 | 4 | 4 |  |  |  |  | 4 | 6 | 6 | 8 | 10 | 10 | [9 empty] | 6 | 8 | 8 | 8 | 8 | 5 |  |  |  | 13 | 44 | 43
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [11 empty] | 2 |  |  | 2 |  |  |  | 2 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 28 | 36
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [24 empty] | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 3 | 2 | 3 | 1 | 3 | 0 | 10 | 24
WP5 | Management |  | 153 | 73 | 224 | 450 | 164 | 36.44% | 30 | 30 | 30 | 32 | 30 | 31 | 30 | 31 | 30 | 28 | 29 | 30 | 30 | 30 | 30 | 43 | 46 | 50 | 55 | 32 | 30 | 29 | 29 | 31 | 30 | 30 | 30 | 32 | 31 | 31 | 30 | 31 | 40 | 44 | 50 | 55 | 361 | 435 | 434
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 14.24% | 35.21% |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 20 | 24 | 28 | 32 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 18 | 22 | 28 | 36 | 192 | 232 | 232
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [6 empty] | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 9 | 8 | 9 | 8 | 9 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 3 | 2 | 92 | 95 | 77
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 24 | 24
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [6 empty] | 3 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 |  |  | 3 | 3 | 3 | 2 | 10 | 10 | 10 | 11 | 3 | 2 |  |  | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 3 | 10 | 14 | 14 | 14 | 26 | 57 | 74
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [6 empty] | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 27 | 27 | 27
|  | Totals | 483.5 | 2369.5 | 307.5 | 3160.5
[5 empty] | check: | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## WP perspective
Summary of hours per WP/task for each partner for Year 1
0 | (or for the months in Year 1 for which data have been provided) |  |  |  |  | Kibbutzim | Mofet | Beit Berl | Kaye | Bucharest | Exeter | Tallin | Gordon | Sakhnin | Talpiot | Salzburg | Total
| All WPs |  |  |  |  | 1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1081
| WP1 | Preparation |  |  |  | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 203
|  | WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9
|  | WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
|  | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
|  | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice |  |  | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12
|  | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation |  |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
|  | WP1.2/T1.2.3 (Mofet) | Implementing detailed work plan and events calendar |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. |  |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
|  | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners |  |  | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
|  | WP1.3/T1.3.1 (Kaye) | Training units for teachers |  |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25
|  | WP1.3/T1.3.2 (Kaye) | Training units for mentors |  |  | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35
|  | WP1.3/T1.3.3 (Kaye) | Teaching units for colleges |  |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
|  | WP1.3/T1.3.4 (Kaye) | Workshops for dissemination |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | WP1.3/T1.3.5 (Kaye) | Pre-service teachers |  |  | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29
|  | WP1.3/T1.3.6 (Kaye) | Policy makers |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  | WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination |  |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| WP2 | Development |  |  |  | 406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 406
|  | WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  |  | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52
|  | WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. |  |  | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
|  | WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice |  |  | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
|  | WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40
|  | WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners |  |  | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62
|  | WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange |  |  | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46
|  | WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. |  |  | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46
|  | WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
|  | WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
|  | WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs |  |  | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20
|  | WP2.2/T2.2.4 (BB) | Implementation of training & workshops events |  |  | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28
| WP3 | Quality Plan |  |  |  | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 68
|  | WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14
|  | WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities |  |  | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
|  | WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … |  |  | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
|  | WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation |  |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
| WP4 | Dissemination & Exploitation |  |  |  | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43
|  | WP4.1/T4.1.1 (Kaye) | Website preparation, launching & maintenance |  |  | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15
|  | WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting |  |  | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
|  | WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… |  |  | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13
|  | WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  | WP4.1/T4.1.5 (Kaye) | Exploitation planning |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5 | Management |  |  |  | 361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 361
|  | WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  |  | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 192
|  | WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. |  |  | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92
|  | WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress |  |  | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24
|  | WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. |  |  | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26
|  | WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems |  |  | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27
|  |  |  | Checks: | All WPs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WP1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WP2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WP3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WP4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | WP5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A2: OWNER: Master check

## P1 - Kibbutzim
Kibbutzim |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 131.5 | 246.5 | 87 | 465 | 465.7333 | 100.2% | 36 | 48 | 80 | 123 | 155 | 124 | 131 | 103 | 97 | 35 | 55 | 94 | 68 | 75 | 100 | 128 | 144 | 127 | 97 | 80 | 81 | 45 | 66 | 96 | 49 | 54 | 67 | 87 | 127 | 156 | 179 | 194 | 86 | 63 | 121 | 122 | 1081 | 1107 | 1305
WP1 | Preparation |  | 15 | 30.5 | 11.5 | 57 | 57.0667 | 100.1% | 2 | 8 | 38 | 44 | 44 | 0 | 0 | 5 | 9 | 0 | 22 | 31 | 4 | 7 | 11 | 7 | 4 | 2 | 4 | 14 | 22 | 5 | 23 | 26 | 8 | 10 | 14 | 8 | 10 | 1 | 8 | 6 | 17 | 2 | 6 | 6 | 203 | 129 | 96
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 12.26% | 12.25% |  |  |  | 2 | 2 | 2 | [5 empty] | 2 | 1 | 1 | 1 | [11 empty] | 2 | 3 | 3 | [8 empty] | 9 | 2 | 8
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [7 empty] | 2 | 2 | 2 | 2 | [5 empty] | 2 | 2 | [13 empty] | 2 | 3 | 3 | [8 empty] | 12 | 0 | 8
K | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [7 empty] | 2 |  |  | 2 | [5 empty] | 2 | 2 |  |  | 2 |  | 2 |  | 2 |  | 2 |  |  | 2 | 2 | 2 | [6 empty] | 2 |  | 2 | 2 | 8 | 10 | 10
I | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [7 empty] | 2 | 2 | 2 | 2 | [5 empty] | 2 | 2 |  | 2 | [8 empty] | 2 | 2 | [12 empty] | 12 | 6 | 0
B | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [8 empty] | 5 | 5 | [6 empty] | 2 | 2 | [7 empty] | 2 | 4 | [10 empty] | 2 | 2 |  |  |  | 14 | 6 | 4
B | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [6 empty] | 2 | 2 | [10 empty] | 1 | 2 | 1 |  | 1 |  | 1 |  | 1 |  |  | 1 | 1 | 1 | [10 empty] | 4 | 8 | 2
U | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [9 empty] | 5 | 6 | [5 empty] | 1 | 2 |  |  | 7 | 7 | [10 empty] | 2 |  | 2 |  | 2 |  | 2 | 2 | 2 | 2 | 14 | 14 | 14
T | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [8 empty] | 6 | 6 | 6 | [7 empty] | 2 | 2 | [22 empty] | 18 | 4 | 0
Z | WP1.3/T1.3.1 (Kaye) | Training units for teachers | [8 empty] | 5 | 5 | 5 | [5 empty] | 5 | 5 | [7 empty] | 4 | 4 |  | 5 | 5 |  |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 25 | 18 | 8
I | WP1.3/T1.3.2 (Kaye) | Training units for mentors | [8 empty] | 5 | 5 | 5 |  |  | 5 | 5 |  | 5 | 5 | [7 empty] | 4 | 4 |  | 5 | 5 |  |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 35 | 18 | 8
M | WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [8 empty] | 2 | 3 | 3 | [5 empty] | 1 | 2 | [7 empty] | 4 | 4 |  | 5 | 5 | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  |  |  | 11 | 18 | 10
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [33 empty] | 2 | 2 |  |  | 2 | 3 |  |  |  | 0 | 0 | 9
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [8 empty] | 7 | 7 | 7 | [6 empty] | 8 | [9 empty] | 4 | 5 | 5 | 1 | 1 |  |  |  | 1 | [6 empty] | 29 | 14 | 3
| WP1.3/T1.3.6 (Kaye) | Policy makers | [10 empty] | 2 |  |  |  | 2 | [5 empty] | 1 |  | 1 |  | 1 |  | 1 | 1 | 1 | 1 | 2 | 2 | [8 empty] | 2 | 2 | 4 | 7 | 8
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [8 empty] | 2 | 2 | 2 |  |  |  | 2 | [8 empty] | 2 |  |  | 2 | [10 empty] | 2 | 2 |  |  |  | 8 | 4 | 4
WP2 | Development |  | 29.5 | 130.5 | 18.5 | 178.5 | 179.0667 | 100.3% | 4 | 10 | 10 | 35 | 66 | 73 | 87 | 48 | 37 | 4 | 4 | 28 | 26 | 26 | 36 | 51 | 66 | 56 | 31 | 26 | 19 | 2 | 9 | 26 | 2 | 1 | 7 | 21 | 62 | 101 | 122 | 131 | 12 | 0 | 52 | 52 | 406 | 374 | 563
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 38.39% | 38.45% | [5 empty] | 8 | 8 | 8 | 10 | 10 |  |  | 8 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |  |  | 5 |  |  |  |  | 10 | 20 | 30 | 40 | 1 |  | 5 | 5 | 52 | 50 | 111
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [10 empty] | 5 | 5 | 4 | 5 | 5 |  |  | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 |  | 1 |  | 1 |  | 1 |  | 1 | 1 |  | 5 | 5 | 28 | 20 | 15
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [10 empty] | 8 | 8 | 6 | 8 | 8 |  |  | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 |  |  |  |  | 10 | 20 | 30 | 40 | 1 |  | 10 | 10 | 44 | 40 | 121
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [6 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |  |  | 4 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 |  |  | 3 | [10 empty] | 5 | 5 | 40 | 30 | 10
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [7 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 4 | 4 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | [12 empty] | 62 | 24 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [9 empty] | 5 | 10 | 12 | 19 | [7 empty] | 10 | 20 | 30 | 20 | [9 empty] | 10 | 20 | 30 | 20 |  | 1 |  | 10 | 5 | 46 | 80 | 96
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [9 empty] | 5 | 10 | 12 | 19 | [5 empty] | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 |  |  | 4 |  |  |  |  | 10 | 20 | 30 | 40 |  |  | 5 | 8 | 46 | 35 | 113
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [9 empty] | 5 | 5 | 5 | 5 | [5 empty] | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 |  |  | 3 | 2 | [8 empty] | 1 |  | 5 | 7 | 20 | 25 | 13
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [9 empty] | 5 | 5 | 5 | 5 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 |  |  | 5 | 10 | 10 | 5 |  |  |  |  | 5 | 5 | 20 | 20 | 40
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [9 empty] | 5 | 5 | 5 | 5 | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | 2 | 2 | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 | 2 | 20 | 20 | 14
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [11 empty] | 3 | 6 | 15 | 4 | [6 empty] | 5 | 10 | 10 | 5 | [10 empty] | 5 | 10 | 10 | 5 |  |  |  | 28 | 30 | 30
WP3 | Quality Plan |  | 8 | 17.5 | 1.5 | 27 | 27.0667 | 100.2% | 0 | 0 | 0 | 8 | 9 | 12 | 7 | 12 | 16 | 2 | 0 | 2 | 2 | 2 | 12 | 15 | 15 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 11 | 11 | 11 | 5 | 6 | 6 | 3 | 3 | 4 | 0 | 68 | 67 | 68
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 5.806% | 5.812% |  |  |  |  | 2 | 3 | 5 |  | 2 | 2 | [5 empty] | 3 | 4 | 4 | [9 empty] | 2 | 2 | 2 | [7 empty] | 14 | 11 | 6
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [9 empty] | 2 | 2 | 2 | 2 | 2 | 3 | [5 empty] | 3 | 4 | 4 | [9 empty] | 3 | 3 | 3 | [7 empty] | 13 | 11 | 9
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [9 empty] | 4 | 4 | 5 | 5 | 6 | 7 | [5 empty] | 3 | 4 | 4 | [9 empty] | 2 | 2 | 2 | [7 empty] | 31 | 11 | 6
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [13 empty] | 2 | 4 | 2 |  | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 4 | 5 | 6 | 6 | 3 | 3 | 4 |  | 10 | 34 | 47
WP4 | Dissemination & Exploitation |  | 10.5 | 27 | 1 | 38.5 | 38.5333 | 100.1% | 0 | 0 | 2 | 4 | 6 | 8 | 7 | 7 | 5 | 1 | 0 | 3 | 6 | 10 | 11 | 12 | 13 | 16 | 4 | 5 | 7 | 6 | 2 | 10 | 5 | 9 | 5 | 15 | 13 | 18 | 13 | 20 | 14 | 14 | 9 | 9 | 43 | 102 | 144
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 8.28% | 8.274% |  |  |  |  | 2 | 3 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 2 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 |  | 3 | 15 | 12 | 18
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [8 empty] | 2 | 2 | 1 | 1 | 1 | 1 | 1 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  | 2 |  | 2 |  | 2 |  | 3 | 4 | 5 | 5 |  | 11 | 8 | 23
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [10 empty] | 2 | 3 | 4 | 4 |  |  |  |  | 4 | 6 | 6 | 8 | 10 | 10 | [9 empty] | 6 | 8 | 8 | 8 | 8 | 5 |  |  |  | 13 | 44 | 43
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [11 empty] | 2 |  |  | 2 |  |  |  | 2 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 28 | 36
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [24 empty] | 1 | 1 | 2 | 2 | 1 | 3 | 2 | 1 | 2 | 1 | 2 | 2 | 2 | 3 | 2 | 3 | 1 | 3 | 0 | 10 | 24
WP5 | Management |  | 68.5 | 41 | 54.5 | 164 | 164 | 100% | 30 | 30 | 30 | 32 | 30 | 31 | 30 | 31 | 30 | 28 | 29 | 30 | 30 | 30 | 30 | 43 | 46 | 50 | 55 | 32 | 30 | 29 | 29 | 31 | 30 | 30 | 30 | 32 | 31 | 31 | 30 | 31 | 40 | 44 | 50 | 55 | 361 | 435 | 434
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 35.27% | 35.21% |  | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 20 | 24 | 28 | 32 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 18 | 22 | 28 | 36 | 192 | 232 | 232
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [6 empty] | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 9 | 8 | 9 | 8 | 9 | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 3 | 2 | 92 | 95 | 77
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [6 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 24 | 24
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [6 empty] | 3 | 3 | 2 | 3 | 2 | 3 | 2 | 3 | 2 |  |  | 3 | 3 | 3 | 2 | 10 | 10 | 10 | 11 | 3 | 2 |  |  | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 3 | 10 | 14 | 14 | 14 | 26 | 57 | 74
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [6 empty] | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 1 | 27 | 27 | 27
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## P2 - Mofet
Mofet |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 113 | 233 | 72 | 418 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | Preparation |  | 15.5 | 32 | 12.5 | 60 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 14.35% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [42 empty] | 0 | 0 | 0
M | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [42 empty] | 0 | 0 | 0
O | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [42 empty] | 0 | 0 | 0
F | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [42 empty] | 0 | 0 | 0
E | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [42 empty] | 0 | 0 | 0
T | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [42 empty] | 0 | 0 | 0
| WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.1 (Kaye) | Training units for teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.2 (Kaye) | Training units for mentors | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.6 (Kaye) | Policy makers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [42 empty] | 0 | 0 | 0
WP2 | Development |  | 28 | 132 | 16.5 | 176.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 42.22% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [42 empty] | 0 | 0 | 0
WP3 | Quality Plan |  | 7 | 17 | 1.5 | 25.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 6.1% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [42 empty] | 0 | 0 | 0
WP4 | Dissemination & Exploitation |  | 8 | 24.5 | 1 | 33.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 8.014% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [42 empty] | 0 | 0 | 0
WP5 | Management |  | 54.5 | 27.5 | 40.5 | 122.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 29.31% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [42 empty] | 0 | 0 | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## P3 - Beit Berl
Beit Berl |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 75 | 234 | 27 | 336 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | Preparation |  | 18 | 36 | 4 | 58 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 17.26% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [42 empty] | 0 | 0 | 0
B | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [42 empty] | 0 | 0 | 0
E | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [42 empty] | 0 | 0 | 0
I | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [42 empty] | 0 | 0 | 0
T | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [42 empty] | 0 | 0 | 0
| WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [42 empty] | 0 | 0 | 0
B | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [42 empty] | 0 | 0 | 0
E | WP1.3/T1.3.1 (Kaye) | Training units for teachers | [42 empty] | 0 | 0 | 0
R | WP1.3/T1.3.2 (Kaye) | Training units for mentors | [42 empty] | 0 | 0 | 0
L | WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.6 (Kaye) | Policy makers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [42 empty] | 0 | 0 | 0
WP2 | Development |  | 30.5 | 145 | 5 | 180.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 53.72% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [42 empty] | 0 | 0 | 0
WP3 | Quality Plan |  | 11 | 22 | 0 | 33 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 9.821% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [42 empty] | 0 | 0 | 0
WP4 | Dissemination & Exploitation |  | 12.5 | 31 | 0 | 43.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 12.95% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [42 empty] | 0 | 0 | 0
WP5 | Management |  | 3 | 0 | 18 | 21 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 6.25% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [42 empty] | 0 | 0 | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## P4 - Kaye
Kaye |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 69.5 | 222 | 25 | 316.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | Preparation |  | 15.5 | 32 | 3 | 50.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 15.96% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [42 empty] | 0 | 0 | 0
K | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [42 empty] | 0 | 0 | 0
A | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [42 empty] | 0 | 0 | 0
Y | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [42 empty] | 0 | 0 | 0
E | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [42 empty] | 0 | 0 | 0
| WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [42 empty] | 0 | 0 | 0
| WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.1 (Kaye) | Training units for teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.2 (Kaye) | Training units for mentors | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.6 (Kaye) | Policy makers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [42 empty] | 0 | 0 | 0
WP2 | Development |  | 24 | 129.5 | 4 | 157.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 49.76% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [42 empty] | 0 | 0 | 0
WP3 | Quality Plan |  | 8 | 17.5 | 0 | 25.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 8.057% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [42 empty] | 0 | 0 | 0
WP4 | Dissemination & Exploitation |  | 19 | 43 | 0 | 62 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 19.59% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [42 empty] | 0 | 0 | 0
WP5 | Management |  | 3 | 0 | 18 | 21 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 6.635% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [42 empty] | 0 | 0 | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## P5 - Bucharest
Bucharest |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 4.5 | 447 | 27 | 478.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | Preparation |  | 0 | 116.5 | 0 | 116.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 24.35% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [42 empty] | 0 | 0 | 0
B | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [42 empty] | 0 | 0 | 0
U | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [42 empty] | 0 | 0 | 0
C | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [42 empty] | 0 | 0 | 0
H | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [42 empty] | 0 | 0 | 0
A | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [42 empty] | 0 | 0 | 0
R | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [42 empty] | 0 | 0 | 0
E | WP1.3/T1.3.1 (Kaye) | Training units for teachers | [42 empty] | 0 | 0 | 0
S | WP1.3/T1.3.2 (Kaye) | Training units for mentors | [42 empty] | 0 | 0 | 0
T | WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.6 (Kaye) | Policy makers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [42 empty] | 0 | 0 | 0
WP2 | Development |  | 0 | 213.5 | 0 | 213.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 44.62% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [42 empty] | 0 | 0 | 0
WP3 | Quality Plan |  | 0 | 47 | 0 | 47 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 9.822% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [42 empty] | 0 | 0 | 0
WP4 | Dissemination & Exploitation |  | 0 | 70 | 0 | 70 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 14.63% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [42 empty] | 0 | 0 | 0
WP5 | Management |  | 4.5 | 0 | 27 | 31.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 6.583% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [42 empty] | 0 | 0 | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## P6 - Exeter
Exeter |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 11 | 144.5 | 4.5 | 160 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | Preparation |  | 0 | 36 | 0 | 36 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 22.5% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [42 empty] | 0 | 0 | 0
E | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [42 empty] | 0 | 0 | 0
X | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [42 empty] | 0 | 0 | 0
E | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [42 empty] | 0 | 0 | 0
T | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [42 empty] | 0 | 0 | 0
E | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [42 empty] | 0 | 0 | 0
R | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.1 (Kaye) | Training units for teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.2 (Kaye) | Training units for mentors | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.6 (Kaye) | Policy makers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [42 empty] | 0 | 0 | 0
WP2 | Development |  | 0 | 66.5 | 0 | 66.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 41.56% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [42 empty] | 0 | 0 | 0
WP3 | Quality Plan |  | 0 | 14 | 0 | 14 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 8.75% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [42 empty] | 0 | 0 | 0
WP4 | Dissemination & Exploitation |  | 0 | 23.5 | 0 | 23.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 14.69% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [42 empty] | 0 | 0 | 0
WP5 | Management |  | 11 | 4.5 | 4.5 | 20 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 12.5% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [42 empty] | 0 | 0 | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## P7 - Tallin
Tallin |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 4.5 | 447 | 27.5 | 479 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | Preparation |  | 0 | 116.5 | 0 | 116.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 24.32% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [42 empty] | 0 | 0 | 0
T | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [42 empty] | 0 | 0 | 0
A | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [42 empty] | 0 | 0 | 0
L | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [42 empty] | 0 | 0 | 0
L | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [42 empty] | 0 | 0 | 0
I | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [42 empty] | 0 | 0 | 0
N | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.1 (Kaye) | Training units for teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.2 (Kaye) | Training units for mentors | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.6 (Kaye) | Policy makers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [42 empty] | 0 | 0 | 0
WP2 | Development |  | 0 | 213.5 | 0 | 213.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 44.57% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [42 empty] | 0 | 0 | 0
WP3 | Quality Plan |  | 0 | 47 | 0 | 47 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 9.812% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [42 empty] | 0 | 0 | 0
WP4 | Dissemination & Exploitation |  | 0 | 70 | 0.5 | 70.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 14.72% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [42 empty] | 0 | 0 | 0
WP5 | Management |  | 4.5 | 0 | 27 | 31.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 6.576% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [42 empty] | 0 | 0 | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## P8 - Gordon
Gordon |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 24.5 | 86 | 10 | 120.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | Preparation |  | 6 | 13 | 0.5 | 19.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 16.18% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [42 empty] | 0 | 0 | 0
G | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [42 empty] | 0 | 0 | 0
O | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [42 empty] | 0 | 0 | 0
R | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [42 empty] | 0 | 0 | 0
D | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [42 empty] | 0 | 0 | 0
O | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [42 empty] | 0 | 0 | 0
N | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.1 (Kaye) | Training units for teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.2 (Kaye) | Training units for mentors | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.6 (Kaye) | Policy makers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [42 empty] | 0 | 0 | 0
WP2 | Development |  | 10.5 | 55.5 | 0.5 | 66.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 55.19% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [42 empty] | 0 | 0 | 0
WP3 | Quality Plan |  | 3 | 7.5 | 0 | 10.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 8.714% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [42 empty] | 0 | 0 | 0
WP4 | Dissemination & Exploitation |  | 4 | 10 | 0 | 14 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 11.62% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [42 empty] | 0 | 0 | 0
WP5 | Management |  | 1 | 0 | 9 | 10 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 8.299% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [42 empty] | 0 | 0 | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## P9 - Sakhnin
Sakhnin |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 24.5 | 86 | 10 | 120.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | Preparation |  | 6 | 13 | 0.5 | 19.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 16.18% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [42 empty] | 0 | 0 | 0
S | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [42 empty] | 0 | 0 | 0
A | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [42 empty] | 0 | 0 | 0
K | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [42 empty] | 0 | 0 | 0
H | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [42 empty] | 0 | 0 | 0
N | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [42 empty] | 0 | 0 | 0
I | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [42 empty] | 0 | 0 | 0
N | WP1.3/T1.3.1 (Kaye) | Training units for teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.2 (Kaye) | Training units for mentors | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.6 (Kaye) | Policy makers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [42 empty] | 0 | 0 | 0
WP2 | Development |  | 10.5 | 55.5 | 0.5 | 66.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 55.19% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [42 empty] | 0 | 0 | 0
WP3 | Quality Plan |  | 3 | 7.5 | 0 | 10.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 8.714% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [42 empty] | 0 | 0 | 0
WP4 | Dissemination & Exploitation |  | 4 | 10 | 0 | 14 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 11.62% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [42 empty] | 0 | 0 | 0
WP5 | Management |  | 1 | 0 | 9 | 10 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 8.299% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [42 empty] | 0 | 0 | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## P10 - Talpiot
Talpiot |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 24.5 | 86 | 10 | 120.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | Preparation |  | 6 | 13 | 0.5 | 19.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 16.18% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [42 empty] | 0 | 0 | 0
T | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [42 empty] | 0 | 0 | 0
A | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [42 empty] | 0 | 0 | 0
L | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [42 empty] | 0 | 0 | 0
P | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [42 empty] | 0 | 0 | 0
I | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [42 empty] | 0 | 0 | 0
O | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [42 empty] | 0 | 0 | 0
T | WP1.3/T1.3.1 (Kaye) | Training units for teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.2 (Kaye) | Training units for mentors | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.6 (Kaye) | Policy makers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [42 empty] | 0 | 0 | 0
WP2 | Development |  | 10.5 | 55.5 | 0.5 | 66.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 55.19% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [42 empty] | 0 | 0 | 0
WP3 | Quality Plan |  | 3 | 7.5 | 0 | 10.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 8.714% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [42 empty] | 0 | 0 | 0
WP4 | Dissemination & Exploitation |  | 4 | 10 | 0 | 14 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 11.62% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [42 empty] | 0 | 0 | 0
WP5 | Management |  | 1 | 0 | 9 | 10 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 8.299% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [42 empty] | 0 | 0 | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## P11- Salzburg
Salzburg |  |  | Budgetted work days |  |  |  | Total plan-ned | Plan-ned as % of budget | Work hours planned for 1st year (2016-17) | [11 empty] | Work hours planned for 2nd year (2017-18) | [11 empty] | Work hours planned for 3rd year (2018-19) | [11 empty] | Total hours planned for
WPs and tasks (leader) |  |  | Mana-ger | Teacher Trainer Resear-cher | Admin. | Total |  |  | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | 1 Oct | 2 Nov | 3 Dec | 4 Jan | 5 Feb | 6 Mar | 7 Apr | 8 May | 9 Jun | 10 Jul | 11 Aug | 12 Sep | Year 1 | Year 2 | Year 3
Total f/all WPs & tasks (red=planned now) |  |  | 1 | 137.5 | 7.5 | 146 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WP1 | Preparation |  | 0 | 35.5 | 0 | 35.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP1.1/ T1.1.1 (Mofet) | Selection of schools |  |  | % effort alloc.: | 24.32% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP1.1/ T1.1.2 (Mofet) | Selection of teachers and mentors | [42 empty] | 0 | 0 | 0
S | WP1.1/ T1.1.3 (Mofet) | Authorities and policy makers | [42 empty] | 0 | 0 | 0
A | WP1.2/T1.2.1 (Mofet) | Establishing the MITs in schools focusing on BTs' voice | [42 empty] | 0 | 0 | 0
L | WP1.2/T1.2.2 (Mofet) | Questionnaires for evaluation | [42 empty] | 0 | 0 | 0
Z | WP1.2/T1.2.3 (Mofet) | Implem. detailed work plan and events calendar | [42 empty] | 0 | 0 | 0
B | WP1.2/T1.2.4 (Mofet) | Means for amplif. BTs' voices in schools & colleges. | [42 empty] | 0 | 0 | 0
U | WP1.2/T1.2.5 (Mofet) | Adapting communic. pltfrm (linked t/website) f/partners | [42 empty] | 0 | 0 | 0
R | WP1.3/T1.3.1 (Kaye) | Training units for teachers | [42 empty] | 0 | 0 | 0
G | WP1.3/T1.3.2 (Kaye) | Training units for mentors | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.3 (Kaye) | Teaching units for colleges | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.4 (Kaye) | Workshops for dissemination | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.5 (Kaye) | Pre-service teachers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.6 (Kaye) | Policy makers | [42 empty] | 0 | 0 | 0
| WP1.3/T1.3.7 (Kaye) | Tools for reflection and self determination | [42 empty] | 0 | 0 | 0
WP2 | Development |  | 0 | 64 | 0 | 64 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP2.1/T2.1.1 (SMK) | Carrying out the MITs in schools |  | % effort alloc.: |  | 43.84% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP2.1/T2.1.2 (SMK) | Carrying out the work between the colleges & the MITs. | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.3 (SMK) | Implementing the means for amplifying BTs' voice | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.4 (SMK) | Contacts between educ. authorities, schools & colleges | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.5 (SMK) | Managing communication platform for all partners | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.6 (SMK) | Workshops & courses f/reflection & knowledge exchange | [42 empty] | 0 | 0 | 0
| WP2.1/T2.1.7 (SMK) | Curriculum & sylabi for teachers' acred. based on MIT exp. | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.1 (BB) | Implementation of new curriculum in colleges | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.2 (BB) | Implementation of curriculum for MITs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.3 (BB) | Implementation of training for mentors and BTs | [42 empty] | 0 | 0 | 0
| WP2.2/T2.2.4 (BB) | Implementation of training & workshops events | [42 empty] | 0 | 0 | 0
WP3 | Quality Plan |  | 0 | 15 | 0 | 15 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP3.1/T3.1.1 (Mofet) | Determin. of QA/QC areas |  | % effort alloc.: |  | 10.27% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP3.1/T3.1.2 (Mofet) | Det. of quality criteria & standards for the diff. activities | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.3 (Mofet) | Quality plan - How activ. will endorse quality criteria … | [42 empty] | 0 | 0 | 0
| WP3.1/T3.1.4 (Mofet) | Quality monitoring and evaluation | [42 empty] | 0 | 0 | 0
WP4 | Dissemination & Exploitation |  | 0 | 23 | 0 | 23 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP4.1/T4.1.1 (Kaye) | Website prep., launching & maint. |  | % effort alloc.: |  | 15.75% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP4.1/T4.1.2 (Kaye) | Dissemination planning and reporting | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.3 (Kaye) | Dissemination activities: Seminars, workshops… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.4 (Kaye) | Establish & maint. a comm. of BTs: Forums, networks… | [42 empty] | 0 | 0 | 0
| WP4.1/T4.1.5 (Kaye) | Exploitation planning | [42 empty] | 0 | 0 | 0
WP5 | Management |  | 1 | 0 | 7.5 | 8.5 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WP5.1/T5.1.1 (SMK/Mofet) | Coord. of partners’ activities in the project. |  | % effort alloc.: |  | 5.822% | #DIV/0! | [37 empty] | 0 | 0 | 0
| WP5.1/T5.1.2 (SMK/Mofet) | Ensuring that mgt procedures are established and implem. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.3 (SMK/Mofet) | Ensuring proj.'s visibility through monitoring progress | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.4 (SMK/Mofet) | Reporting and maintaining a fluent link with PO in Europe. | [42 empty] | 0 | 0 | 0
| WP5.1/T5.1.5 (SMK/Mofet) | Minimiz. of risks via timely identif. & resol. of problems | [42 empty] | 0 | 0 | 0
D1.1.1
D1.2.1
D1.3.1
D2.1.1
D2.1.2
D2.1.3a
D2.1.3b
D2.1.3c
D2.1.4
D2.2.1
D2.2.2a
D2.2.2b
D2.2.2c
D3.1.1
D4.1.1
D4.1.2
D4.1.3
D5.1.1a
D5.1.1b
D1.3.2

## Sheet1
Plan-ned as % of budget